## Checklist
Migrating from Asana to Vaiz: Step-by-Step Guide
Maren Holst, Senior Reviewer · 13.03.2026
✓ | Step | Section
☐ | Active projects with tasks updated in the last 60 days — primary migration target. | Pre-Migration Audit
☐ | Active automation Rules with execution in the last 30 days — rebuild list. | Pre-Migration Audit
☐ | Connected integrations (Slack, Salesforce, GitHub, Zapier) — reconnection list. | Pre-Migration Audit
☐ | CSV export — per-project, includes tasks, custom fields, assignees, due dates, status. | Exporting Data from Asana
☐ | JSON export — through the Asana API, supports attachments and richer field types. | Exporting Data from Asana
☐ | Bulk export — through the Asana data export tool on Enterprise tier. | Exporting Data from Asana
☐ | List every active Asana Rule with its trigger, conditions, and actions. | Rebuilding Workflows in Vaiz
☐ | For each Rule, build the equivalent Vaiz When-then chain with conditional branching. | Rebuilding Workflows in Vaiz
☐ | Test in a staging project before applying workspace-wide. | Rebuilding Workflows in Vaiz
☐ | Run both products\' rules in parallel for one week to catch divergence. | Rebuilding Workflows in Vaiz
☐ | Vaiz publishes a structured onboarding flow with role-based starter paths. | Team Rollout and Change Management
☐ | Most non-technical hires reach productive use within 2-4 hours of focused training. | Team Rollout and Change Management
☐ | Power users transitioning from Asana need 1-2 days to find the equivalent shortcuts. | Team Rollout and Change Management
☐ | Roughly 5-10% of a migration\'s value gets spent on consultant or internal-engineering hours that the original plan didn\'t account for. | Migration Timeline and Cost
☐ | Productivity drops 10-20% during the parallel-run period as users learn the new tool. | Migration Timeline and Cost
☐ | Both costs are recoverable within one quarter of the sunset date. | Migration Timeline and Cost
Full article: https://vaizvsasana.com/migrating-from-asana-to-vaiz
Asana vs Vaiz may earn referral fees when readers sign up for Vaiz. Editorial recommendations are based on public vendor information, pricing pages, and buyer-fit analysis.